## RTM
Requirement / Scenario ID | Requirement / Functional Area | Requirement Objective | Priority | Test Case IDs | Total TCs | Passed | Failed | Blocked | Not Run | Coverage Status | Defect IDs | Defect Status
S1 | User Authentication | Verify that users can successfully register, verify their accounts, and log in. | High | TC-S1-001, TC-S1-002, TC-S1-003, TC-S1-004, TC-S1-005, TC-S1-006, TC-S1-007, TC-S1-008 | 8 | 8 | 0 | 0 | 0 | Covered - All Passed | DID-S1-001, DID-S1-002 | Open / Unresolved
S2 | Password Reset & OTP Flows | Verify that users can securely recover and reset their passwords. | High | TC-S2-001, TC-S2-002, TC-S2-003, TC-S2-004, TC-S2-005, TC-S2-009 | 6 | 6 | 0 | 0 | 0 | Covered - All Passed |  | No defect recorded
S3 | Post Management | Verify the complete lifecycle of user posts. | High | TC-S3-001, TC-S3-002, TC-S3-003, TC-S3-004, TC-S3-005, TC-S3-006, TC-S3-007, TC-S3-008, TC-S3-009, TC-S3-010 | 10 | 10 | 0 | 0 | 0 | Covered - All Passed | DID-S3-001 | Open / Unresolved
S4 | Comments, Likes & Feed Updates | Verify user interactions with posts and real-time/updated feed behavior. | High | TC-S4-001, TC-S4-002, TC-S4-004, TC-S4-005, TC-S4-006, TC-S4-007, TC-S4-008, TC-S4-009 | 8 | 8 | 0 | 0 | 0 | Covered - All Passed |  | No defect recorded
S5 | Bookmarks | Verify that users can save and manage posts using bookmarks. | Medium | TC-S5-001, TC-S5-002, TC-S5-003, TC-S5-004, TC-S5-005, TC-S5-006, TC-S5-007 | 7 | 5 | 2 | 0 | 0 | Covered - Failures Present | DID-S5-001, DID-S5-002 | Open / Unresolved
S6 | Real-Time Chat | Verify reliable real-time communication and message persistence. | High | TC-S6-001, TC-S6-002, TC-S6-003, TC-S6-004, TC-S6-005, TC-S6-006, TC-S6-007, TC-S6-008, TC-S6-009, TC-S6-010 | 10 | 10 | 0 | 0 | 0 | Covered - All Passed |  | No defect recorded
S7 | Event Management | Verify event creation, management, discovery, and RSVP functionality. | Medium | TC-S7-001, TC-S7-002, TC-S7-003, TC-S7-004, TC-S7-005, TC-S7-006, TC-S7-007, TC-S7-008, TC-S7-009, TC-S7-010 | 10 | 10 | 0 | 0 | 0 | Covered - All Passed |  | No defect recorded
S8 | Profile Management | Verify profile viewing, editing, and privacy-related fields. | Medium | TC-S8-001, TC-S8-002, TC-S8-003, TC-S8-004, TC-S8-005, TC-S8-006, TC-S8-007, TC-S8-008 | 8 | 8 | 0 | 0 | 0 | Covered - All Passed |  | No defect recorded
S9 | API Failure & Resilience | Verify that the application handles backend failures and invalid requests gracefully. | High | TC-S9-001, TC-S9-002, TC-S9-003, TC-S9-004, TC-S9-005, TC-S9-006, TC-S9-007, TC-S9-008, TC-S9-009, TC-S9-010 | 10 | 8 | 2 | 0 | 0 | Covered - Failures Present | DID-S9-001, DID-S9-002 | Open / Unresolved
S10 | Authorization Enforcement | Verify that protected resources can only be accessed by authorized users. | High | TC-S10-001, TC-S10-002, TC-S10-003, TC-S10-004, TC-S10-005, TC-S10-006, TC-S10-007, TC-S10-008, TC-S10-009 | 9 | 9 | 0 | 0 | 0 | Covered - All Passed |  | No defect recorded
S11 | Cross-Browser & Responsive UI | Verify consistent application behavior and layout across supported browsers and screen sizes. | Medium | TC-S11-001, TC-S11-002, TC-S11-003, TC-S11-004, TC-S11-005, TC-S11-006, TC-S11-007, TC-S11-008 | 8 | 8 | 0 | 0 | 0 | Covered - All Passed |  | No defect recorded
S12 | Accessibility | Verify that the main application flows are usable and accessible to users with different accessibility needs. | Medium | TC-S12-001, TC-S12-002, TC-S12-004, TC-S12-005, TC-S12-006, TC-S12-007, TC-S12-008, TC-S12-010 | 8 | 8 | 0 | 0 | 0 | Covered - All Passed |  | No defect recorded
Traceability Note
The supplied Test Plan/Test Scenarios do not define separate requirement IDs. Scenario IDs (S1–S12) are therefore used as the traceability requirement/functional-area identifiers.

## Coverage Summary
Metric | Value
Test cases in Test Cases sheet | 102
Passed | 98
Failed | 4
Blocked | 0
Not Run | 0
Pass Rate | 96.08%
Scenarios Covered | 12
Open / Unresolved Defects | 7

## Defect Traceability
Defect ID | Related Test Case | Scenario ID | Test Case Title | Test Status | Priority | Severity | Expected Result | Actual Result | Remarks | Defect Status
DID-S1-001 | TC-S1-002 | S1 | Verify signup with invalid or incomplete information | Pass | High | Low | Signup is rejected and clear validation feedback is displayed. | Although sign-up was rejected, clear validation feedback was not displayed. | Only the non-match was password was displayed. | Open / Unresolved
DID-S1-002 | TC-S1-006 | S1 | Verify login failure with invalid credentials | Pass | High | Low | Login is rejected and an appropriate error message is displayed. | Although log-in was rejected, clear validation feedback was not displayed. | Clear and concise email or password mismatch is not provided. | Open / Unresolved
DID-S3-001 | TC-S3-008 | S3 | Verify deletion of a post | Pass | High | Medium | The post is deleted successfully. | The post is deleted successfully only when the user visits their profile page. | The post deletion in the feed page is not successful. | Open / Unresolved
DID-S5-001 | TC-S5-002 | S5 | Verify unbookmarking a post | Fail | Medium | High | The post is removed from bookmarks successfully. | The post is not removed from bookmark. |  | Open / Unresolved
DID-S5-002 | TC-S5-005 | S5 | Verify removed bookmarks no longer appear in saved posts | Fail | Medium | High | The removed post no longer appears in saved posts. | The post is not removed from bookmark. |  | Open / Unresolved
DID-S9-001 | TC-S9-001 | S9 | Verify application behavior when database is unavailable | Fail | High | High | The application handles the database failure gracefully without crashing. | The application crashes and the user is logged out. |  | Open / Unresolved
DID-S9-002 | TC-S9-002 | S9 | Verify API behavior when database connection is lost | Fail | High | Medium | The API returns an appropriate error response and does not expose unnecessary internal details. | The API is timed-out but unnecessary internal details is not exposed. |  | Open / Unresolved